# Project brief for Hoosier Goose Co.: "Somebody Did It First", Shorts batch 1

Updated 2026-10-09 by the Claude Code session building it. This goes alongside the main brief (Somebody Did It First - Cowork brief.md).

# What it is

Four Shorts, 45–60 seconds each, voiced by Gus himself (a phone voice memo is fine).

Two jobs:

1. Set the brand's sound. They're the voice test that led to the podcast format, where Gus hosts in his own voice.

2. Promotion. Once the podcast is live, Shorts and Reels clips are the main way new listeners find it (see production/podcast/PODCAST-PLAN.md).

Why Gus voices them. It's the same workflow as Lumber Counter Talk and Heavier Runners. Gus records, Claude builds the visuals to his timing, and his recordings also surface fact problems and new ideas.

# The four Shorts

| # | Title | The famous name | Who did it first | Status |
| --- | --- | --- | --- | --- |
| 01 | Before Stephenson | George Stephenson and Rocket (1829); Vanderbilt for US viewers | Richard Trevithick: a steam locomotive on rails in south Wales, 1804 | Script ready. Same story as podcast Episode 1, so it can work as its trailer. |
| 02 | The Doctor Boston Forgot | Boston's "Ether Day", 1846 | Crawford Long, Georgia, 30 March 1842. National Doctors' Day is on his date. | Script ready. Facts solid, no hedge needed. |
| 02b | (alternate) Japan, 1804 | Same as 02 | Hanaoka Seishu: general anesthesia with an herbal mix, 1804, "by the Japanese calendar of the time" | Fact sheet only. Optional. |
| 03 | The Pizza Letter | The 1889 Queen Margherita story and the palace thank-you letter | Historian Zachary Nowak (2014) says the letter is probably fake, and a Naples writer described similar pizzas in 1858 | ON HOLD. Record it if Gus likes, but don't post. |
| 04 | Crapper Didn't | Thomas Crapper "invented the toilet" | Sir John Harington's flushing toilet (1596); Alexander Cumming's S-bend patent (1775) | Script ready. Keep the "may" in the slang origin. |

# Hold on Short 03 (and the pizza podcast episode)

It doesn't get posted until three checks are done:

Nowak's 2014 paper is pulled.

The 1858 Naples text (Usi e costumi di Napoli e contorni) is pulled.

An 1880 newspaper item about a Giovanni Brandi and the queen is checked against the story.

Hedges that must stay:

"probably" fake;

"likely" the Brandi family;

not proven.

# Rules for every Short (from the channel memory file)

Voice.

Plain talk; say each point once; assume the viewer knows basic history.

No "right?" and no asides.

Banned words: "genuinely", "dive in", "game changer", "unpack", "in today's video", "level up".

Facts.

Every fact on the fact sheets has its source listed.

Keep each Short's hedge exactly as written.

Each sheet has a "stay away from" list: for example the Trevithick bet story, surgery detail, and Minoan "roof cisterns".

Fair credit. The famous person gets their real due. Crapper "made toilets better"; the Stephensons built what lasted.

Visuals.

Real photos, period prints, maps and the running time bar.

No AI "photos" of real people or events.

No cartoon reconstructions of historical machines; Gus rejected those twice.

On-screen text never says more than the narration.

Credits. Every image is credited in the description.

# The workflow

Gus records all four, one take each, named 01–04, and sends them in the Claude Code chat.

Claude builds each vertical (9:16) Short to Gus's timing: real images, the time bar, burned-in captions, and the source credit. Then a check pass against the fact sheet.

Gus approves and posts to YouTube Shorts, Instagram Reels and TikTok, with sources in the description.

What Gus's takes reveal (pacing, phrasing he changed, facts that sounded off) gets written into the channel memory file and feeds the podcast prep sheets.

# Timing (proposal)

Hold posting until the podcast launches, then use the Shorts to point people to the episodes. Short 01 goes with Episode 1 (Trevithick). The others go with their matching episodes, or as stand-alone teasers in the weeks between.

# Later batches

The podcast's "Legend or Fact?" round (quick true/false claims, then the reveal) is built to be cut straight into Shorts. Once episodes are recorded, that's the main source of new Shorts.

# Where the files are

Repo thunderbob34-boop/osprey, branch research/somebody-did-it-first:

| What | Path |
| --- | --- |
| Scripts to read aloud, with pronunciations | production/shorts/batch-01-voice-scripts.md |
| The same scripts as a Word doc | production/shorts/Somebody Did It First - Shorts Batch 1.docx |
| Fact sheets: hook, facts with sources, hedges, what to avoid | production/shorts/batch-01-fact-sheets.md |
| Channel rules and open items | Somebody Did It First - memory.md |

# Open items waiting on Gus

Record Shorts 01, 02 and 04, and 03 too if he wants (it's held from posting).

Decide whether 02b (Japan) gets made as a follow-up Short.

Confirm the posting timing: hold for the podcast launch, or post sooner to start building an audience.